## WEB
Work Items (Epics/Stories/Tasks) | Jira Ticket | Sprint Count | SPRINT | Necessity Want vs Need | Feasibility Unrealistic vs Possible | Viability Temporary vs Long Term | Frequency 50% Occurrence + 50% #Users Affected | Alternatives Available workarounds | CUSTOMER VALUE | Criticality How urgently does it need to be addressed? | Bonus Value How valuable are the extra benefits, if any? | COST OF DELAY | Execution Time How much time/efforts will it take? | WSJF SCORE 9+ = bypass | ADJUSTED WSJF SCORE based on Sprint Count
|  |  |  | 5 | 5 | 5 | 5 | 4 | 4.8 | 3 | 1 | 8.8 | 2 | 4.4 | 4.4
[9 empty] | 0 |  |  | 0 |  | #DIV/0! | #DIV/0!
WEB Sprint - 2025-May-13
[9 empty] | 0 |  |  | 0 |  | #DIV/0! | #DIV/0!
[9 empty] | 0 |  |  | 0 |  | #DIV/0! | #DIV/0!
[9 empty] | 0 |  |  | 0 |  | #DIV/0! | #DIV/0!
[9 empty] | 0 |  |  | 0 |  | #DIV/0! | #DIV/0!
Note on E1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Scale: 1 through 5 1 = Want, Nonessential 2.5 = Unknown 5 = Need, Essential
Note on F1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Scale: 1 through 5 1 = Unrealistic, Challenging 2.5 = Unknown 5 = Possible, Easy
Note on G1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Scale: 1 through 5 1 = Temporary, Impractical 2.5 = Unknown 5 = Long Term, Practical
Note on H1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Scale: 1 through 5 1 = Rare, Few Users 2.5 = Unknown 5 = Frequent, Many Users
Note on I1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Scale: 1 through 5 1 = Multiple Alternatives 2.5 = Unknown 5 = No Alternative
Note on J1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: ( C +D +E +F +G ) / 5
Note on K1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Scale: 1 through 5 1 = Minimal Revenue Penalty, Mild Client Pressure/Competitor Landscape 2.5 = Unknown 5 = Severe Revenue Penalty, Intense Client Pressure/Competitor Landscape
Note on L1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Scale: 1 through 5 1 = Low Value, Negligible Opportunities 2.5 = Unknown 5 = High Value, Substantial Opportunities
Note on M1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: ( H + I + J )
Note on N1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Scale: 1 through 5 1 = Quick, Simple 2.5 = Unknown 5 = Lengthy, Challenging Consideration: Vacations, holidays, ... etc.
Note on P1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The WSJF Score prioritizes work items based on value, urgency, and risk. ( K / L )

## Mobile
Work Items (Epics/Stories/Tasks) | Jira Ticket | Sprint Count | SPRINT | Necessity Want vs Need | Feasibility Unrealistic vs Possible | Viability Temporary vs Long Term | Frequency 50% Occurrence + 50% #Users Affected | Alternatives Available workarounds | CUSTOMER VALUE | Criticality How urgently does it need to be addressed? | Bonus Value How valuable are the extra benefits, if any? | COST OF DELAY | Execution Time How much time/efforts will it take? | WSJF SCORE 7.5+ = bypass | ADJUSTED WSJF SCORE based on Sprint Count
2024-MAY-16 (bi-weekly #328 + others):
[9 empty] | 0 |  |  | 0 |  | #DIV/0! | #DIV/0!
[9 empty] | 0 |  |  | 0 |  | #DIV/0! | #DIV/0!
2024-MAY-14 (bi-weekly #327 + others): | WEB-26698
Remove color selection limitation from B&S | MOB-9597 | [7 empty] | 0 |  |  | 0 |  | #DIV/0! | #DIV/0!
Sort By Distance when no location selected don't show alert message as Android | MOB-7987 |  |  | 5 | 5 | 5 | 3 | 5 | 4.6 | 3 | 1 | 8.6 | ? | #VALUE! | #VALUE!
Create Prototype, Allowing You To Draw MLS Listings AND Parcels | MOB-5595 | [7 empty] | 0 |  |  | 0 |  | #DIV/0! | #DIV/0!
Centris Trackers Errors | MOB-9600 | [7 empty] | 0 |  |  | 0 |  | #DIV/0! | #DIV/0!
2024-MAY-09 (bi-weekly #326 + others): | WEB-26679
2024-MAY-07 (bi-weekly #325 + others): | WEB-26627
Inconsistent Behavior of Autocomplete When Searching With MLS Area Values | MOB-9573 |  |  | 5 | 5 | 5 | 5 | 2.5 | 4.5 | 4 | 1 | 9.5 | 2 | 4.75 | 4.75
MOBILE Sprint - 2024-MAY-06
2024-MAY-02 (bi-weekly #324 + others): | WEB-26552
MLS-Client Login UI Seem Slightly Aligned to The Right | MOB-9550 |  |  | 2.5 | 5 | 5 | 5 | 1 | 3.7 | 1 | 1 | 5.7 | 1.5 | 3.8 | 3.8
2024-APR-30 (bi-weekly #323 + others): | WEB-26510
2024-APR-25 (bi-weekly #322 + others): | WEB-26495
2024-APR-23 (bi-weekly #321 + others): | WEB-26371
MOBILE Sprint - 2024-APR-22
2024-APR-18 (bi-weekly #320 + others): | WEB-26329
2024-APR-16 (bi-weekly #319 + others): | WEB-26268
MLS# Search display the previously searched listing (only on iOS 16.x devices) | MOB-9543 |  |  | 5 | 5 | 5 | 2 | 1 | 3.6 | 2.5 | 1 | 7.1 | ? | #VALUE! | #VALUE! | Bypassed
Cannot type more than 8 characters in some location search fields | MOB-9514 |  |  | 5 | 5 | 5 | 5 | 3 | 4.6 | 4 | 1 | 9.6 | 1 | 9.6 | 9.6 | Bypassed
2024-APR-11 (bi-weekly #318 + others): | WEB-26246
IOS - Smooth the minimize of the keyboard | MOB-9492 |  |  | 4 | 1 | 5 | 2.5 | 5 | 3.5 | 2 | 1 | 6.5 | ? | #VALUE! | #VALUE! | Won't do as per Patrice
Centris - Price reduction/augmentation tags are displayed inconsistently | MOB-9493 | [7 empty] | 0 |  |  | 0 |  | #DIV/0! | #DIV/0! | Discussion w/ Product Team Required
2024-APR-09 (bi-weekly #317 + others): | WEB-26180
(Epic) ITSO/RAHB - Display "Suppressed" When SuppressSalesPriceYN=Y | MOB-9391 | [7 empty] | 0 |  |  | 0 |  | #DIV/0! | #DIV/0! | Discussion w/ Product Team Required
MOBILE Sprint - 2024-APR-08
2024-APR-04 (bi-weekly #316 + others): | WEB-26140
Implement option to share the external listing URL | MOB-9479 |  |  | 1 | 5 | 5 | 5 | 2 | 3.6 | 1.5 | 1 | 6.1 | 1.5 | 4.0667 | 4.0667
2024-APR-02 (bi-weekly #315 + others): | WEB-26130
2024-MAR-28 (bi-weekly #314 + others): | WEB-26116
(Epic) ITSO/RAHB - Display "Suppressed" When SuppressSalesPriceYN=Y | MOB-9391 | [7 empty] | 0 |  |  | 0 |  | #DIV/0! | #DIV/0! | Moved up in spreadsheet
2024-MAR-26 (bi-weekly #313 + others): | WEB-26034
Centris - Didomi Change | MOB-9421 | [7 empty] | 0 |  |  | 0 |  | #DIV/0! | #DIV/0!
MOBILE Sprint - 2024-MAR-25
2024-MAR-21 (bi-weekly #312 + others): | WEB-26002
Elements we need to have id's on (to avoid using absolute xpath) | MOB-9384 |  |  | 4 | 5 | 5 | 4 | 5 | 4.6 | 3 | 4 | 11.6 | 1 | 11.6 | 11.6
2024-MAR-19 (bi-weekly #311 + others): | WEB-25932
2024-MAR-14 (bi-weekly #310 + others): | WEB-25900
2024-MAR-12 (bi-weekly #309 + others): | WEB-25853
2024-MAR-07 (bi-weekly #308 + others): | WEB-25832 | [9 empty] | 2
0
2024-MAR-05 (bi-weekly #307 + others):
2024-FEB-18 to 2024-MAR-02 (includes bi-weekly #303-#306):
Bi-weekly Support Discussion (#300, 301, & 302):
CRM QA for OREB (Preprod):
Outstanding WEB Issues:
Note on E1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Scale: 1 through 5 1 = Want, Nonessential 2.5 = Unknown 5 = Need, Essential
Note on F1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Scale: 1 through 5 1 = Unrealistic, Challenging 2.5 = Unknown 5 = Possible, Easy
Note on G1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Scale: 1 through 5 1 = Temporary, Impractical 2.5 = Unknown 5 = Long Term, Practical
Note on H1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Scale: 1 through 5 1 = Rare, Few Users 2.5 = Unknown 5 = Frequent, Many Users
Note on I1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Scale: 1 through 5 1 = Multiple Alternatives 2.5 = Unknown 5 = No Alternative
Note on J1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: ( C +D +E +F +G ) / 5
Note on K1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Scale: 1 through 5 1 = Minimal Revenue Penalty, Mild Client Pressure/Competitor Landscape 2.5 = Unknown 5 = Severe Revenue Penalty, Intense Client Pressure/Competitor Landscape
Note on L1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Scale: 1 through 5 1 = Low Value, Negligible Opportunities 2.5 = Unknown 5 = High Value, Substantial Opportunities
Note on M1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: ( H + I + J )
Note on N1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Scale: 1 through 5 1 = Quick, Simple 2.5 = Unknown 5 = Lengthy, Challenging Consideration: Vacations, holidays, ... etc.
Note on O1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The WSJF Score prioritizes work items based on value, urgency, and risk. ( K / L )
Note on P1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The WSJF Score prioritizes work items based on value, urgency, and risk. ( K / L )

## Instructions
Type |  | Necessity Want vs Need | Feasibility Unrealistic vs Possible | Viability Temporary vs Long Term | Frequency 50% Occurrence + 50% #Users Affected | Alternatives Available workarounds | Criticality How urgently does it need to be addressed? | Bonus Value How valuable are the extra benefits, if any? | Execution Time How much time/efforts will it take?
Bugs | 1 | Resolution is nonessential | Resolution is challenging, if not unrealistic | Temporary resolution, doesn't address the root cause | Low occurrence + low #users affected | Multiple workarounds | No penalty, no pressure, no time constraint | No bonus value/opportunity | Higher team velocity, high capacity, fully staffed, simple request
| 2.5 |  | Unknown |  |  | Unknown
| 5 | Issue is a game stopper | Resolution is possible and easy | Fixes the issue permanently | High occurrence + high #users affected | No workaround | Penalties from multiple factors, high pressure to fix, deadline-driven | Multiple bonus values/opportunities | Lower team velocity, low capacity, understaffed, sizable request
MLS Support (Data & Continuity Changes) | 1 | Low impact, non-critical, non-urgent | Unsupported by code/config | Addresses the request/issue temporary, doesn't address the root cause | Low occurrence + low #users affected | Multiple workarounds | No penalty, no pressure, no time constraint | No bonus value/opportunity | Higher team velocity, high capacity, fully staffed, simple request
| 2.5 |  |  |  |  | Unknown
| 5 | High impact, critical, time-sensitive | Supported by existing code/config |  | High occurrence + high #users affected | No workaround | Penalties from multiple factors, high pressure to fix, deadline-driven | Multiple bonus values/opportunities | Lower team velocity, low capacity, understaffed, sizable request
New Client Implementation | 1 | Small client, no time constraint, low revenue potential | Unsupported by code/config | Single-use, custom development, temporary |  | Parallel MLS environment | No penalty, no pressure, no time constraint | No bonus value/opportunity
| 2.5 |  |  |  |  | Unknown
| 5 | Large client, deadline-driven, high revenue potential | Supported by existing code/config | Repeatable, template-based, long term | All end-users | No alternative | Penalties from multiple factors, high pressure to deliver, deadline-driven | Multiple bonus values/opportunities | Lower team velocity, low capacity, understaffed, sizable request
Support (End User Support, Stats, CRM Teams, Internal Tools, ... etc.) | 1 | Nonessential, low impact, no time constraint, low revenue loss/potential | Unprecedented manual intervention, unsupported by code/config, no existing tools/scripts | Temporary, doesn't address the root cause, not supported by code/config, no existing tools/scripts | Low occurrence + low #users affected | Multiple workarounds | No penalty, no pressure, no time constraint | No bonus value/opportunity | Higher team velocity, high capacity, fully staffed, simple request
| 2.5 |  |  |  |  | Unknown
| 5 | Critical, high impact, deadline-driven, high revenue loss/potential | Common manual intervention, supported by existing code/config, existing tools/scripts | Permanent, supported by existing code/config, existing tools/scripts | High occurrence + high #users affected | No workaround | Penalties from multiple factors, high pressure to fix, deadline-driven | Multiple bonus values/opportunities | Lower team velocity, low capacity, understaffed, sizable request
Note on C1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Scale: 1 through 5 1 = Want, Nonessential 2.5 = Unknown 5 = Need, Essential
Note on D1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Scale: 1 through 5 1 = Unrealistic, Challenging 2.5 = Unknown 5 = Possible, Easy
Note on E1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Scale: 1 through 5 1 = Temporary, Impractical 2.5 = Unknown 5 = Long Term, Practical
Note on F1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Scale: 1 through 5 1 = Rare, Few Users 2.5 = Unknown 5 = Frequent, Many Users
Note on G1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Scale: 1 through 5 1 = Multiple Alternatives 2.5 = Unknown 5 = No Alternative
Note on H1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Scale: 1 through 5 1 = Minimal Revenue Penalty, Mild Client Pressure/Competitor Landscape 2.5 = Unknown 5 = Severe Revenue Penalty, Intense Client Pressure/Competitor Landscape
Note on I1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Scale: 1 through 5 1 = Low Value, Negligible Opportunities 2.5 = Unknown 5 = High Value, Substantial Opportunities
Note on J1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Scale: 1 through 5 1 = Quick, Simple 2.5 = Unknown 5 = Lengthy, Challenging Consideration: Vacations, holidays, ... etc.

## Conversion Tables
Conversion Tables
Mobile |  | WEB
Story Points | WSJF | Story Points | WSJF
0.5 | 0.5 | 1 | 1
1 | 1 | 2 to 3 | 2
2 | 1.5 | 4 to 5 | 3
3 to 4 | 2 | 6 to 8 | 4
5 to 7 | 3 | 9 to 12 | 5
8 to 12 | 4
9 to 13 | 5

## To Discuss
Jira Tickets |  |  | Other Topics
Google sync creates multiple duplicate contacts in Prospects CRM | WEB-24868 | Determine fix w/ MAJ of root cause | Ticket Definition of Ready Presentation - To be scheduled on week of May 13th?
Centris - Price reduction/augmentation tags are displayed inconsistently | MOB-9493 | MAJ input required | Centris Meetup - To be scheduled on week of ?
(Epic) ITSO/RAHB - Display "Suppressed" When SuppressSalesPriceYN=Y | MOB-9391 | MAJ input required | Postman OIDC Testing Collections - Doesn't seem to work anymore (reported by Jonathan)
MLS# Search display the previously searched listing (only on iOS 16.x devices) | MOB-9543 | Determine fix for root cause | NJMLS (Flex) Postman RETS Collection - Needs to duplcate some of the RETS collections, because we need to replace something to make it work. | https://rets-njmls.xmlsweb.com/rets/GetMetadata?Type=METADATA-CLASS
"My Favorites" and "Saved Search" in the mobile apps are lost because they are reassigned (like the Match! results/searches) when removing a user from a team with option "Reassign to admin" | WEB-25840 | MAJ input required | Add Philippe as tester for Centris.ca Android App - leblanc.philippe@gmail.com OP-2040 vs WEB-20240 ?
Maris - "RoomLevel" Value Display Adjustment | WEB-26518 | Ticket not ready as per Rolf
Canopy - Listing 4106993 documents incorrectly linked | WEB-25644 | See "to do" in my comment | Remove Bypass privileges for most?
Do we need to import document descriptions from Media? | OP-2040 | We did it for Canopy but might want to do it for the other boards.
Reimport desc for older listings from before the fix 3.35 | WEB-20240 | see Rolf's comment
Rename rets properties file according to well-known code for collection of boards | WEB-23751 | MAJ input required
NWMLS - Setup in PREPROD/STAGING k:webview document module | WEB-26166 | MAJ input required