## How to Use
API INTEGRATION PLANNING TEMPLATE
Get engineering, security, legal and your partner aligned before the first API call
PM Toolkit by Neelesh Singh · neeleshpmtoolkit.com
What this is
A planning doc for any system-to-system integration — partner API, internal service, or third-party platform. It captures the contract, the data mapping, the security and legal posture, and a go-live gate, so the hard questions are answered on paper before they’re expensive in code.
How to use it
1. Open “Integration Plan — Example”: Meterly connecting to a payment provider’s card-updater and recovery webhooks — the integration that actually powers Smart Dunning.
2. Work top to bottom. Overview → objects → auth & security → reliability → environments → test plan → go-live. The security and legal rows exist so nobody discovers a DPA gap the week of launch.
3. Use “Endpoints & Data Mapping” for the contract itself — every call you’ll make and every field that moves, with its transform rule. This is what you hand engineering.
4. The go-live checklist gates the launch: readiness only hits 100% when every applicable item is Done.
Make it yours
Works for REST, webhooks, GraphQL, file/SFTP or event streams — the fields are method-agnostic. Drop in your auth model, your compliance regime (PCI, SOC 2, GDPR, HIPAA), and your environments.
Colour legend
Blue = your input. Black = calculated. Status cells colour by value; the go-live gate turns green only when applicable items are Done.
© PM Toolkit by Neelesh Singh · neeleshpmtoolkit.com — Free for personal use. Adapt freely; please keep the credit line.

## Integration Plan — Example
INTEGRATION PLAN · METERLY × ACME PAYMENTS
PSP card-updater & recovery webhooks — powers Smart Dunning
PM Toolkit by Neelesh Singh · neeleshpmtoolkit.com
OVERVIEW
| Integration name | PSP Card-Updater & Recovery Webhooks
| Systems | Meterly ↔ Acme Payments (payment service provider)
| Direction | Bi-directional (REST out + webhooks in)
| Trigger / sync | Real-time webhooks + nightly card-updater batch
| Business goal | Detect expiring cards, auto-update them, and retry failed charges — the engine behind Smart Dunning v1
| Owner | Lena (PM — Payments) · Marco (eng lead)
| Partner contact | Acme solutions engineering · sol-eng@acme.example
| Target go-live | Jul 8, 2026
DATA OBJECTS & EVENTS
| Object / event | Direction | Operation | Frequency | Notes
| Customer | Inbound | Read | On demand | Match to Meterly account
| Payment method | Both | Read / update | Real-time + batch | Card meta only — never the full PAN
| Charge | Both | Read / retry | Real-time | Retry uses idempotency key
| Webhook: payment.failed | Inbound | Event | Real-time | Opens a dunning sequence
| Webhook: card.updated | Inbound | Event | Real-time | Re-attempts the failed charge
| Webhook: charge.recovered | Inbound | Event | Real-time | Closes the dunning sequence
AUTH & SECURITY
| Auth method | OAuth2 client-credentials (REST) + HMAC-SHA256 signed webhooks
| Secrets storage | Vault; rotated quarterly; no secrets in source or logs
| PII / PCI scope | Tokenised PANs only — SAQ-A scope; store last4 + expiry, never full card
| Data residency | US + EU regions; EU events stay in-region
| DPA / legal status | DPA signed; sub-processor list updated; security review booked
RELIABILITY
| Rate limits | 100 req/s REST; 429 → exponential backoff + jitter
| Retry / backoff | Charge retries on day 1/3/5/7; webhook deliveries retried with backoff
| Idempotency | Idempotency-Key on retry & charge; webhooks deduped on event id
| Error handling | Dead-letter queue for failed webhooks; daily reconciliation vs PSP report
| Monitoring & alerts | Alerts on webhook lag, signature failures, and recovery-rate drop
ENVIRONMENTS
| Environment | Base URL |  | Credentials owner
| Sandbox | sandbox.acme.example/v1 |  | Marco
| Staging | staging-api.acme.example/v1 |  | Marco
| Production | api.acme.example/v1 |  | Eng on-call
TEST PLAN
| Test case | Type | Status | Expected result
| Happy path: failed charge → retry → recovered | Functional | Pass | charge.recovered fires; invoice marked paid
| Pre-dunning: expiring card → reminder sent | Functional | Pass | reminder + secure update link delivered
| Invalid webhook signature rejected | Security | Pass | 401; event not processed
| Rate limit 429 → backoff | Resilience | In progress | retries succeed within SLA
| Duplicate webhook → idempotent | Resilience | Not started | no double-processing
| Reconciliation vs PSP daily report | Data | Not started | zero unexplained deltas
GO-LIVE CHECKLIST
| Go-live readiness | 16.67% | ← green only when every applicable item is Done
| Item / sign-off | Owner | Status | Notes
| Engineering sign-off (contract + error handling) | Marco | Not started
| Security review passed | Security | In progress
| Legal / DPA confirmed | Legal | Done
| Partner UAT complete | Acme | In progress
| Runbook + rollback (kill switch) ready | Dvij | Not started
| Monitoring & alerts live | Marco | Not started
© PM Toolkit by Neelesh Singh · neeleshpmtoolkit.com — Free for personal use. Adapt freely; please keep the credit line.

## Endpoints & Mapping — Example
ENDPOINTS & DATA MAPPING · METERLY × ACME
The contract: every call and every field that moves
PM Toolkit by Neelesh Singh · neeleshpmtoolkit.com
ENDPOINT REGISTER
| Endpoint | Method | Path | Auth | Request (key fields) | Response | Rate limit
| Get customer | GET | /v1/customers/{id} | OAuth2 | id | customer object | 100/s
| Get payment method | GET | /v1/payment_methods/{id} | OAuth2 | id | last4, exp, brand | 100/s
| Enroll card-updater | POST | /v1/card_updater/enroll | OAuth2 | account_id | enrollment id | 50/s
| Retry charge | POST | /v1/charges/{id}/retry | OAuth2 + Idempotency-Key | charge id | charge result | 50/s
| Webhook: payment.failed | POST | (in) /webhooks/acme | HMAC-SHA256 | event payload | 200 OK | —
| Webhook: card.updated | POST | (in) /webhooks/acme | HMAC-SHA256 | event payload | 200 OK | —
| Webhook: charge.recovered | POST | (in) /webhooks/acme | HMAC-SHA256 | event payload | 200 OK | —
FIELD MAPPING
| Source field | Dir | Target field | Type | Transform / rule | Req? | Notes
| acme.customer.id | → | meterly.account_id | string | direct match | Yes
| acme.payment_method.exp_month / exp_year | → | meterly.payment_method.expiry | date | combine → YYYY-MM | Yes
| acme.payment_method.last4 | → | meterly.payment_method.last4 | string | display only | No | no full PAN
| acme.event.type | → | meterly.dunning.trigger | enum | failed→open, recovered→close, updated→retry | Yes
| acme.charge.id | ↔ | meterly.invoice.charge_ref | string | direct | Yes
| acme.charge.failure_code | → | meterly.dunning.reason | enum | map codes → reasons | No | for support view
© PM Toolkit by Neelesh Singh · neeleshpmtoolkit.com — Free for personal use. Adapt freely; please keep the credit line.

## Integration Plan — Blank
INTEGRATION PLAN · [SYSTEM A × SYSTEM B]
Plan the integration before the first call
PM Toolkit by Neelesh Singh · neeleshpmtoolkit.com
OVERVIEW
Integration name
Systems
Direction
Trigger / sync
Business goal
Owner
Partner contact
Target go-live
DATA OBJECTS & EVENTS
| Object / event | Direction | Operation | Frequency | Notes
AUTH & SECURITY
Auth method
Secrets storage
PII / PCI scope
Data residency
DPA / legal status
RELIABILITY
Rate limits
Retry / backoff
Idempotency
Error handling
Monitoring & alerts
ENVIRONMENTS
| Environment | Base URL |  | Credentials owner
TEST PLAN
| Test case | Type | Status | Expected result
GO-LIVE CHECKLIST
| Go-live readiness | 0% | ← green only when every applicable item is Done
| Item / sign-off | Owner | Status | Notes
© PM Toolkit by Neelesh Singh · neeleshpmtoolkit.com — Free for personal use. Adapt freely; please keep the credit line.

## Endpoints & Mapping — Blank
ENDPOINTS & DATA MAPPING · [INTEGRATION]
Document the contract and the field map
PM Toolkit by Neelesh Singh · neeleshpmtoolkit.com
ENDPOINT REGISTER
| Endpoint | Method | Path | Auth | Request (key fields) | Response | Rate limit
FIELD MAPPING
| Source field | Dir | Target field | Type | Transform / rule | Req? | Notes
© PM Toolkit by Neelesh Singh · neeleshpmtoolkit.com — Free for personal use. Adapt freely; please keep the credit line.