## How to Use
EPIC & USER STORY WRITING KIT
Break an epic into stories developers love to build — clear value, testable criteria, less rework
PM Toolkit by Neelesh Singh · neeleshpmtoolkit.com
What this is
A backlog-ready kit: write an epic, split it into user stories with a forced structure (persona → capability → benefit), attach Given/When/Then acceptance criteria, and prioritise — plus a one-page reference for the craft (INVEST, story splitting, Definition of Ready/Done).
How to use it
1. Open “Epic → Stories — Example”. It breaks Meterly’s Smart Dunning v1 epic into real stories with real acceptance criteria — the same work the sprint and business-case templates reference.
2. Fill the three blue parts of each story (As a … / I want to … / so that …). The full story sentence assembles itself in the next column — paste it straight into Jira or Linear.
3. Write acceptance criteria as Given / When / Then. If you can’t, the story isn’t ready — that’s the point.
4. Keep “Writing Reference” open while you split. It’s the difference between stories that flow and stories that bounce back.
Make it yours
Personas, priority scheme (MoSCoW here — swap for your own) and estimate scale are all editable. The story structure and AC pattern are universal; the example domain is not — replace it with yours.
Colour legend
Blue = your input. Black = auto-assembled or calculated. Status cells colour by value.
© PM Toolkit by Neelesh Singh · neeleshpmtoolkit.com — Free for personal use. Adapt freely; please keep the credit line.

## Epic → Stories — Example
EPIC → STORIES · METERLY
Smart Dunning v1 — recover failed payments
PM Toolkit by Neelesh Singh · neeleshpmtoolkit.com
| Epic | Smart Dunning v1 — recover revenue lost to failed payments
| Problem / outcome | ~7.2% of renewal charges fail and we recover only ~48%; lift recovery toward 65%+ without manual chasing.
| Success metric | Failed-payment recovery rate 48% → 65% on the pilot cohort
| Linked objective | Become the billing platform mid-market SaaS can’t afford to churn from
USER STORIES
| ID | As a… (persona) | I want to… (capability) | so that… (benefit) | User story (auto) | Acceptance criteria (Given / When / Then) | Priority | Est | Status
| SD-101 | billing operations lead | have failed charges retried on an adaptive schedule | we recover revenue without manual chasing | As a billing operations lead, I want to have failed charges retried on an adaptive schedule, so that we recover revenue without manual chasing. | Given a charge fails When the retry engine runs Then it retries on the configured schedule (e.g. day 1/3/5/7) and stops on success or after N attempts | Must | 5 | In progress
| SD-102 | finance admin | have customers prompted to update an expiring card before it fails | fewer payments fail in the first place | As a finance admin, I want to have customers prompted to update an expiring card before it fails, so that fewer payments fail in the first place. | Given a card expires within 30 days When the pre-dunning job runs Then the customer gets an email + in-app banner with a secure update link | Must | 5 | In review
| SD-103 | customer with a failed payment | update my card in one click | I can fix a failed payment in seconds | As a customer with a failed payment, I want to update my card in one click, so that I can fix a failed payment in seconds. | Given I open the update link When I submit a valid card Then the failed charge retries immediately and I see confirmation | Must | 8 | In progress
| SD-104 | product manager | track recovery rate against a control cohort | we can prove the lift is real | As a product manager, I want to track recovery rate against a control cohort, so that we can prove the lift is real. | Given the pilot is live When I open the dashboard Then I see recovery rate for pilot vs control over time | Should | 3 | In progress
| SD-105 | support agent | see a customer’s dunning status | I can answer “why did my payment fail?” without escalating | As a support agent, I want to see a customer’s dunning status, so that I can answer “why did my payment fail?” without escalating. | Given I open an account Then I see last failure reason, retry schedule and recovery status | Could | 3 | Backlog
| SUMMARY | 5 stories · 18 Must pts · 24 total pts
© PM Toolkit by Neelesh Singh · neeleshpmtoolkit.com — Free for personal use. Adapt freely; please keep the credit line.

## Writing Reference
WRITING REFERENCE
The craft, on one page — keep it open while you write
PM Toolkit by Neelesh Singh · neeleshpmtoolkit.com
THE FORMAT
| Structure | As a [persona], I want to [capability], so that [benefit]. The persona is a role, not “user”. The benefit is the why — it’s what you’ll measure.
| Strong | As a finance admin, I want expiring-card reminders, so that fewer payments fail.
| Weak | As a user, I want a cron job that scans the tokens table. (a solution, no persona, no value)
INVEST — a good story is…
| Independent | Can ship on its own; minimise dependencies on other stories.
| Negotiable | A conversation starter, not a contract — the how is decided with the team.
| Valuable | Delivers value to a user or the business; if you can’t name the value, cut it.
| Estimable | The team can size it; if they can’t, you need a spike or more detail first.
| Small | Fits comfortably inside one sprint — ideally a few days.
| Testable | You can write Given/When/Then for it; untestable means undefined.
ACCEPTANCE CRITERIA (Given / When / Then)
| Pattern | Given [context], When [action], Then [observable outcome]. One scenario per behaviour; add scenarios for edge cases.
| Example | Given a card expires within 30 days, When the pre-dunning job runs, Then the customer receives a reminder with a secure update link.
| Rule-style | For simple stories, a checklist of rules works too — just keep each rule observable and unambiguous.
SPLITTING A STORY THAT’S TOO BIG (SPIDR)
| Spike | Time-boxed research first when the team can’t estimate.
| Paths | Split by workflow path — happy path now, alternates later.
| Interfaces | Split by UI/surface — API first, then web, then mobile.
| Data | Split by data type or variation — one card type, then more.
| Rules | Relax business rules — ship the core, add validations next.
DEFINITION OF READY (before it enters a sprint)
| Checklist | Clear persona & value · acceptance criteria written · dependencies known · design/te ch questions answered · sized by the team · small enough for one sprint.
DEFINITION OF DONE (before you call it shipped)
| Checklist | Code reviewed & merged · tests pass · acceptance criteria met · docs/changelog updated · observability in place · demoed & accepted by PM.
ANTI-PATTERNS TO AVOID
| Watch for | Writing the solution instead of the need · “As a user…” (be specific) · stories with no measurable benefit · estimating before AC exist · epics masquerading as stories.
© PM Toolkit by Neelesh Singh · neeleshpmtoolkit.com — Free for personal use. Adapt freely; please keep the credit line.

## Epic → Stories — Blank
EPIC → STORIES · [PRODUCT]
Break the epic into testable stories
PM Toolkit by Neelesh Singh · neeleshpmtoolkit.com
Epic
Problem / outcome
Success metric
Linked objective
USER STORIES
| ID | As a… (persona) | I want to… (capability) | so that… (benefit) | User story (auto) | Acceptance criteria (Given / When / Then) | Priority | Est | Status
| SUMMARY | 0 stories · 0 Must pts · 0 total pts
© PM Toolkit by Neelesh Singh · neeleshpmtoolkit.com — Free for personal use. Adapt freely; please keep the credit line.