## Start Here
PRIORITIZATION SCORING MATRIX
How to use this matrix
PM Toolkit by Neelesh Singh · neeleshpmtoolkit.com
What this is
Two lenses on the same backlog, side by side. RICE gives you an objective, math-driven score; the weighted model lets you encode what YOUR business values; the quadrant turns it into a picture. Edit only the blue cells — every score, rank and quadrant recalculates itself.
1) RICE (developed by Sean McBride at Intercom)
| Reach | How many accounts/users this affects per quarter. Use real data.
| Impact | Per-account impact: 3 = massive, 2 = high, 1 = medium, 0.5 = low, 0.25 = minimal.
| Confidence | How sure are you? 100% = data-backed, 80% = some data, 50% = a guess. Below 50% is a moonshot.
| Effort | Total person-months across product, design & engineering. The only factor that divides.
| Score | RICE = (Reach × Impact × Confidence) ÷ Effort. Higher = more impact per unit of effort. Sort high → low.
2) Weighted scoring (when strategy matters as much as math)
Rate each initiative 1–5 on five criteria, then set the weights (they must total 100%). The weighted value (0–100) reflects your strategy — useful when a low-RICE item is strategically essential (e.g. compliance that unlocks a market). Compare the RICE rank and the weighted rank: where they disagree is exactly where the interesting product conversation lives.
3) Value vs Effort quadrant
| Quick win | High value, low effort — do first.
| Big bet | High value, high effort — plan and resource.
| Fill-in | Low value, low effort — only with slack.
| Time sink | Low value, high effort — avoid or defer.
How to use the file
• ‘RICE + Weighted — Example’: a fictional billing & payments SaaS (“Meterly”) with 10 real-feeling initiatives already scored.
• ‘Value-Effort Quadrant’: the same data plotted. Watch the quick wins separate from the time sinks.
• ‘RICE + Weighted — Blank’: your turn. Type into the blue cells; everything else is automatic.
• Re-score at the start of each planning cycle — confidence and effort change as you learn.
© PM Toolkit by Neelesh Singh · neeleshpmtoolkit.com — Free for personal use. Adapt freely; please keep the credit line.

## RICE + Weighted — Example
PRIORITIZATION SCORING MATRIX
RICE + weighted scoring + Value/Effort quadrant — it ranks itself
PM Toolkit by Neelesh Singh · neeleshpmtoolkit.com
SET YOUR THRESHOLDS & WEIGHTS
| Quick-win cutoffs: | Value ≥ | 60 | Effort (PM) ≤ | 4
RICE = (Reach × Impact × Confidence) ÷ Effort. Impact 3=massive,2=high,1=med,0.5=low,0.25=min. Confidence 100/80/50%.
# | Initiative | Reach (accounts/qtr) | Impact (0.25–3) | Confidence | Effort (person-mo) | RICE score | RICE rank | Strategic fit | Revenue impact | Customer / retention value | Compliance / risk | Feasibility / confidence | Weighted value (0–100) | Wtd rank | Value/Effort quadrant
| Criteria weights → (edit blue; must total 100%) | [6 empty] | 25% | 25% | 20% | 15% | 15% | 100% | (=100%?)
1 | Self-serve card update (pre-dunning) | 1500 | 2 | 100% | 1.5 | 2000 | 1 | 4 | 4 | 5 | 3 | 5 | 84 | 3 | Quick win
2 | Webhook reliability + API status dashboard | 2000 | 1 | 100% | 1 | 2000 | 1 | 3 | 2 | 4 | 2 | 5 | 62 | 8 | Quick win
3 | Smart Dunning v1 (retries + card-updater) | 1200 | 3 | 80% | 4 | 720 | 3 | 5 | 5 | 5 | 4 | 4 | 94 | 1 | Quick win
4 | Usage-metering accuracy (pipeline v2) | 800 | 2 | 100% | 3 | 533.3333 | 4 | 4 | 3 | 5 | 3 | 5 | 79 | 5 | Quick win
5 | AI-assisted recovery (adaptive) | 1200 | 3 | 50% | 6 | 300 | 5 | 5 | 5 | 4 | 3 | 2 | 81 | 4 | Big bet
6 | SAML SSO + audit logs | 200 | 2 | 80% | 2 | 160 | 6 | 4 | 3 | 3 | 4 | 4 | 71 | 7 | Quick win
7 | SEPA Direct Debit + multi-currency (EU) | 300 | 3 | 50% | 6 | 75 | 7 | 5 | 5 | 4 | 5 | 3 | 90 | 2 | Big bet
8 | Revenue recognition (ASC 606) | 150 | 3 | 50% | 8 | 28.125 | 8 | 5 | 4 | 3 | 5 | 2 | 78 | 6 | Big bet
9 | Embedded payments / pay-by-bank (A2A) | 500 | 2 | 25% | 9 | 27.7778 | 9 | 4 | 4 | 3 | 2 | 1 | 61 | 9 | Big bet
10 | Multi-entity consolidation | 80 | 2 | 50% | 7 | 11.4286 | 10 | 3 | 3 | 3 | 2 | 2 | 54 | 10 | Time sink
© PM Toolkit by Neelesh Singh · neeleshpmtoolkit.com — Free for personal use. Adapt freely; please keep the credit line.

## Value-Effort Quadrant
VALUE VS EFFORT QUADRANT
Plotted from the Example tab — Value (weighted score) vs Effort
PM Toolkit by Neelesh Singh · neeleshpmtoolkit.com
| Key |  | Quadrants
| 1 | Self-serve card update (pre-dunning) | Quick win | High value, low effort — do these first.
| 2 | Webhook reliability + API status dashboard | Big bet | High value, high effort — plan & resource properly.
| 3 | Smart Dunning v1 (retries + card-updater) | Fill-in | Low value, low effort — do if there's slack.
| 4 | Usage-metering accuracy (pipeline v2) | Time sink | Low value, high effort — avoid / defer.
| 5 | AI-assisted recovery (adaptive)
| 6 | SAML SSO + audit logs
| 7 | SEPA Direct Debit + multi-currency (EU)
| 8 | Revenue recognition (ASC 606)
| 9 | Embedded payments / pay-by-bank (A2A)
| 10 | Multi-entity consolidation
© PM Toolkit by Neelesh Singh · neeleshpmtoolkit.com — Free for personal use. Adapt freely; please keep the credit line.

## RICE + Weighted — Blank
PRIORITIZATION SCORING MATRIX
RICE + weighted scoring + Value/Effort quadrant — it ranks itself
PM Toolkit by Neelesh Singh · neeleshpmtoolkit.com
SET YOUR THRESHOLDS & WEIGHTS
| Quick-win cutoffs: | Value ≥ | 60 | Effort (PM) ≤ | 4
RICE = (Reach × Impact × Confidence) ÷ Effort. Impact 3=massive,2=high,1=med,0.5=low,0.25=min. Confidence 100/80/50%.
# | Initiative | Reach (accounts/qtr) | Impact (0.25–3) | Confidence | Effort (person-mo) | RICE score | RICE rank | Strategic fit | Revenue impact | Customer / retention value | Compliance / risk | Feasibility / confidence | Weighted value (0–100) | Wtd rank | Value/Effort quadrant
| Criteria weights → (edit blue; must total 100%) | [6 empty] | 25% | 25% | 20% | 15% | 15% | 100% | (=100%?)
1
2
3
4
5
6
7
8
9
10
11
12
© PM Toolkit by Neelesh Singh · neeleshpmtoolkit.com — Free for personal use. Adapt freely; please keep the credit line.