## Start Here
PRODUCT ROADMAP CANVAS
How to use this canvas
PM Toolkit by Neelesh Singh · neeleshpmtoolkit.com
What this is
A Now / Next / Later roadmap. Unlike a dated Gantt chart, the three columns are CONFIDENCE HORIZONS, not quarters. Pioneered by Janna Bastow (ProdPad) and popularised by Teresa Torres, the format trades false precision for honesty: you commit to what you know now and stay flexible about what you don't.
The three horizons
| NOW | Validated, scoped, in active development. High confidence you're solving the right problem with a viable approach. Hard external deadlines (regulatory/contractual) attach HERE, to a specific item.
| NEXT | Problem is well-defined; you're exploring solutions and running discovery. Medium confidence. No delivery date yet — that's the point.
| LATER | Strategic bets you believe will matter but that need real discovery. Low confidence. Often just a problem statement. May change or drop.
The two rules that make it work
1. Tie every item to an OBJECTIVE and a target METRIC. The roadmap is a plan for outcomes, not a feature wishlist. If you can't name the outcome, it isn't ready.
2. The organising question is never “what quarter?” It's “how important is this problem, and how much do we know about solving it?” Items move Later → Next → Now as confidence grows.
How to use the file
• Read the ‘Roadmap — Example’ tab first: a fictional Series-B billing & payments SaaS (“Meterly”) reasoned across all three horizons.
• Work in ‘Roadmap — Blank’. Type straight into the cards; copy a card block to add more.
• Capture raw ideas in ‘Backlog’ — it feeds your Later column once a signal is strong enough.
Confidence key
| High | Discovery done; evidence is quantitative; team agrees on the approach.
| Medium | Problem clear; some evidence; solution still being explored.
| Low | A bet. Mostly assumption. Needs discovery before it earns a Now/Next slot.
Method credit: Now/Next/Later — Janna Bastow & Simon Cast, ProdPad. Outcome-based roadmapping — Teresa Torres.
© PM Toolkit by Neelesh Singh · neeleshpmtoolkit.com — Free for personal use. Adapt freely; please keep the credit line.

## Roadmap — Example
PRODUCT ROADMAP CANVAS
Now / Next / Later — organised by confidence, not calendar dates
PM Toolkit by Neelesh Singh · neeleshpmtoolkit.com
| NOW |  | NEXT |  | LATER
| DOING · high confidence · in active development |  | DISCOVERING · medium confidence · in discovery / scoping |  | DREAMING · strategic bets · low confidence, needs discovery
| Smart Dunning v1 — intelligent retries + card-updater |  | SEPA Direct Debit + multi-currency (EU local payments) |  | AI-assisted recovery (adaptive retry timing + routing)
| Objective (problem / outcome) | Stop losing customers to failed payments (involuntary churn) they never chose. | Objective (problem / outcome) | Unlock EU mid-market — today we can't collect the way EU buyers pay. | Objective (problem / outcome) | Move from rules to ML — become best-in-class at recovery.
| Target metric / KPI | Lift failed-payment recovery from ~48% (industry median) to 65%+ on pilot cohort. | Target metric / KPI | Open EU pipeline; first EU ARR within 2 quarters of GA. | Target metric / KPI | Push recovery toward 70–85% (vs 47.6% median).
| Confidence | High — 9 design partners + Recurly/ProfitWell benchmarks. | Confidence | Medium — discovery underway; PSD2/SCA compliance scoping. | Confidence | Low — a bet; needs ML discovery + data volume.
| Evidence / signal | 7.2% of renewal charges fail today; expired cards = 42% of failures. | Evidence / signal | 18 inbound EU prospects stalled on lack of SEPA. | Evidence / signal | AI recovery platforms report 70–85% in 2025 benchmarks.
| Status / note | In build — pilot this cycle. | Status / note | Discovery — compliance + PSP scoping. | Status / note | Horizon — needs discovery.
| Self-serve card update in billing portal (pre-dunning) |  | Revenue recognition (ASC 606) automation |  | Embedded payments / pay-by-bank (A2A)
| Objective (problem / outcome) | Prevent failures before they happen by prompting card updates pre-expiry. | Objective (problem / outcome) | Remove the finance blocker that stops us moving upmarket. | Objective (problem / outcome) | New revenue line and lower processing cost via open banking.
| Target metric / KPI | Prevent 35–40% of expiring-card failures before the charge. | Target metric / KPI | Unblock enterprise deals that require automated rev-rec. | Target metric / KPI | New take-rate revenue stream; reduced PSP fees.
| Confidence | High — scoped; Stripe card-account-updater integration. | Confidence | Medium — exploring build vs. partner. | Confidence | Low — market timing unclear.
| Evidence / signal | Pre-dunning notices prevent 35–40% of failures (Stripe data). | Evidence / signal | Lost 3 enterprise deals in 2 quarters citing rev-rec gaps. | Evidence / signal | Strong A2A / open-banking momentum in EU.
| Status / note | In build. | Status / note | Discovery. | Status / note | Horizon.
| Usage-metering accuracy (event pipeline v2) |  | SAML SSO + audit logs (enterprise readiness) |  | Multi-entity consolidation (global finance teams)
| Objective (problem / outcome) | Earn trust in usage-based invoices; kill billing disputes. | Objective (problem / outcome) | Pass enterprise security review without exceptions. | Objective (problem / outcome) | Serve multinational customers billing across entities/currencies.
| Target metric / KPI | Billing disputes < 0.5% of invoices. | Target metric / KPI | Security-questionnaire pass rate on first submission ↑. | Target metric / KPI | Expansion into multinational accounts.
| Confidence | High — root-caused; design done. | Confidence | Medium — well understood, not yet scheduled. | Confidence | Low — only early signal.
| Evidence / signal | #1 support driver in customer QBRs. | Evidence / signal | Recurring blocker in enterprise procurement. | Evidence / signal | Requested by 2 large prospects.
| Status / note | In build. | Status / note | Discovery. | Status / note | Horizon.
© PM Toolkit by Neelesh Singh · neeleshpmtoolkit.com — Free for personal use. Adapt freely; please keep the credit line.

## Roadmap — Blank
PRODUCT ROADMAP CANVAS
Now / Next / Later — organised by confidence, not calendar dates
PM Toolkit by Neelesh Singh · neeleshpmtoolkit.com
| NOW |  | NEXT |  | LATER
| DOING · high confidence · in active development |  | DISCOVERING · medium confidence · in discovery / scoping |  | DREAMING · strategic bets · low confidence, needs discovery
| ‹ Initiative — the problem you're solving › |  | ‹ Initiative — the problem you're solving › |  | ‹ Initiative — the problem you're solving ›
| Objective (problem / outcome) | ‹ What outcome / problem? Tie to a business objective › | Objective (problem / outcome) | ‹ What outcome / problem? Tie to a business objective › | Objective (problem / outcome) | ‹ What outcome / problem? Tie to a business objective ›
| Target metric / KPI | ‹ How will you know it worked? (metric / KPI) › | Target metric / KPI | ‹ How will you know it worked? (metric / KPI) › | Target metric / KPI | ‹ How will you know it worked? (metric / KPI) ›
| Confidence | ‹ High / Medium / Low › | Confidence | ‹ High / Medium / Low › | Confidence | ‹ High / Medium / Low ›
| Evidence / signal | ‹ Data, research or signal behind this › | Evidence / signal | ‹ Data, research or signal behind this › | Evidence / signal | ‹ Data, research or signal behind this ›
| Status / note | ‹ In build / Discovery / Horizon › | Status / note | ‹ In build / Discovery / Horizon › | Status / note | ‹ In build / Discovery / Horizon ›
| ‹ Initiative — the problem you're solving › |  | ‹ Initiative — the problem you're solving › |  | ‹ Initiative — the problem you're solving ›
| Objective (problem / outcome) | ‹ What outcome / problem? Tie to a business objective › | Objective (problem / outcome) | ‹ What outcome / problem? Tie to a business objective › | Objective (problem / outcome) | ‹ What outcome / problem? Tie to a business objective ›
| Target metric / KPI | ‹ How will you know it worked? (metric / KPI) › | Target metric / KPI | ‹ How will you know it worked? (metric / KPI) › | Target metric / KPI | ‹ How will you know it worked? (metric / KPI) ›
| Confidence | ‹ High / Medium / Low › | Confidence | ‹ High / Medium / Low › | Confidence | ‹ High / Medium / Low ›
| Evidence / signal | ‹ Data, research or signal behind this › | Evidence / signal | ‹ Data, research or signal behind this › | Evidence / signal | ‹ Data, research or signal behind this ›
| Status / note | ‹ In build / Discovery / Horizon › | Status / note | ‹ In build / Discovery / Horizon › | Status / note | ‹ In build / Discovery / Horizon ›
| ‹ Initiative — the problem you're solving › |  | ‹ Initiative — the problem you're solving › |  | ‹ Initiative — the problem you're solving ›
| Objective (problem / outcome) | ‹ What outcome / problem? Tie to a business objective › | Objective (problem / outcome) | ‹ What outcome / problem? Tie to a business objective › | Objective (problem / outcome) | ‹ What outcome / problem? Tie to a business objective ›
| Target metric / KPI | ‹ How will you know it worked? (metric / KPI) › | Target metric / KPI | ‹ How will you know it worked? (metric / KPI) › | Target metric / KPI | ‹ How will you know it worked? (metric / KPI) ›
| Confidence | ‹ High / Medium / Low › | Confidence | ‹ High / Medium / Low › | Confidence | ‹ High / Medium / Low ›
| Evidence / signal | ‹ Data, research or signal behind this › | Evidence / signal | ‹ Data, research or signal behind this › | Evidence / signal | ‹ Data, research or signal behind this ›
| Status / note | ‹ In build / Discovery / Horizon › | Status / note | ‹ In build / Discovery / Horizon › | Status / note | ‹ In build / Discovery / Horizon ›
© PM Toolkit by Neelesh Singh · neeleshpmtoolkit.com — Free for personal use. Adapt freely; please keep the credit line.

## Backlog — Example
DISCOVERY BACKLOG
Raw ideas & signals — graduate the strong ones into the Later column
PM Toolkit by Neelesh Singh · neeleshpmtoolkit.com
Idea / opportunity | Problem it might solve | Linked objective | Evidence / signal | Confidence | Suggested horizon | Notes
In-app failed-payment banner | Customers don't know a charge failed until churn | Reduce involuntary churn | Support tickets after silent failures | Medium | Next | Pair with Smart Dunning
Dunning analytics dashboard | Finance can't see recovery performance | Trust & expansion | Asked in 6 QBRs | Medium | Next | Add-on candidate
Localised invoices (tax/VAT) | EU invoices need VAT formatting | EU expansion | Tied to SEPA discovery | Medium | Later | Depends on EU work
Crypto / stablecoin payout | A few prospects asked | New segment | 2 prospect mentions | Low | Later | Watch, don't build
Self-serve plan migration | Manual plan changes burn CS time | Efficiency / NRR | CS time logs | Medium | Later | Quantify CS hours
© PM Toolkit by Neelesh Singh · neeleshpmtoolkit.com — Free for personal use. Adapt freely; please keep the credit line.

## Backlog — Blank
DISCOVERY BACKLOG
Raw ideas & signals — graduate the strong ones into the Later column
PM Toolkit by Neelesh Singh · neeleshpmtoolkit.com
Idea / opportunity | Problem it might solve | Linked objective | Evidence / signal | Confidence | Suggested horizon | Notes
© PM Toolkit by Neelesh Singh · neeleshpmtoolkit.com — Free for personal use. Adapt freely; please keep the credit line.