## How to Use
RELEASE NOTES & LAUNCH CHECKLIST
Coordinate every team, catch the edge cases, and tell customers what changed — in one place
PM Toolkit by Neelesh Singh · neeleshpmtoolkit.com
What this is
Two artefacts for shipping safely: a cross-functional launch checklist with a live Go / No-Go readiness gate, and a clean release-notes template your customers (or your team) will actually read.
How to use it
1. Open “Launch Checklist — Example” — Meterly launching Smart Dunning v1 across product, eng, QA, security, support, marketing and data. Readiness % and the Go / No-Go verdict update as you set each status.
2. Assign every item an owner and a due date. Mark anything irrelevant as N/A so it doesn’t drag your readiness down. Blocked items turn the gate red until cleared.
3. Draft the customer story in “Release Notes — Example” while you build — not the night before. Lead with the benefit, not the feature.
4. Copy the “— Blank” tabs per release. Add or delete workstream rows to match how your org actually ships.
Make it yours
The workstreams are a strong default, not gospel — add Mobile, Localisation, Finance, Trust & Safety, or whatever your launch needs. The readiness maths counts every item that isn’t marked N/A.
Colour legend
Blue = your input. Black = calculated. Status cells colour by value; the Go / No-Go gate is green only when everything applicable is Done.
© PM Toolkit by Neelesh Singh · neeleshpmtoolkit.com — Free for personal use. Adapt freely; please keep the credit line.

## Launch Checklist — Example
LAUNCH CHECKLIST · METERLY
Smart Dunning v1 — launch readiness
PM Toolkit by Neelesh Singh · neeleshpmtoolkit.com
| Release / version | Smart Dunning v1 · 2026.06
| Target launch date | Jul 8, 2026
| Release owner | Lena (PM — Payments)
| Launch tier | Major — new revenue capability
READINESS
| Overall readiness | 34.48% | Go / No-Go | Not ready
CHECKLIST (by workstream)
| Item | Owner | Status | Due | Notes
Product
| Pilot success criteria met (recovery ≥ 60% vs control) | Lena | Done | Jul 1
| Pricing & packaging for the add-on finalised | Lena | In progress | Jul 3
| Rollout plan (pilot → cohort → GA) approved | Lena | Done | Jul 1
Engineering
| Feature flag + kill switch tested in prod | Marco | Done | Jul 2
| Retry engine load/perf check at 2× peak | Dvij | In progress | Jul 4
| Idempotency verified on retry + charge | Marco | Done | Jul 2
| Rollback runbook written & dry-run | Dvij | Not started | Jul 5
QA
| Edge cases pass: declined, expired, network, partial | Aisha | In progress | Jul 5
| Webhook signature + replay tests | Aisha | Done | Jul 2
| Regression on core billing flows | Aisha | Not started | Jul 6
Security & Compliance
| PCI scope review — tokenised, no PAN stored (SAQ-A) | Security | Done | Jun 28
| DPA with PSP signed | Legal | Done | Jun 25
| Pen-test findings closed | Security | In progress | Jul 4
Docs
| Help-center: “Update a failed payment” article | Docs | In progress | Jul 4
| API changelog + webhook events documented | Docs | Not started | Jul 5
Support / CS
| Macros for “why did my payment fail?” | CS Lead | Not started | Jul 6
| CS trained on dunning status view | CS Lead | In progress | Jul 5
| Escalation path for stuck recoveries defined | CS Lead | Done | Jul 1
Marketing
| Release notes finalised | Marketing | In progress | Jul 6
| Customer announcement email scheduled | Marketing | Not started | Jul 7
| In-app announcement / changelog post | Marketing | Not started | Jul 8
Sales
| Renewal talk-track + one-pager updated | Sales Eng | Not started | Jul 7
| Pricing sheet updated for the add-on | Sales Eng | N/A |  | Handled in pricing tool
Data & Analytics
| Recovery dashboard live (pilot vs control) | Lena | Done | Jul 1
| Event tracking verified end-to-end | Dvij | In progress | Jul 4
| Control cohort defined & locked | Lena | Done | Jul 1
Go / No-Go sign-offs
| Engineering sign-off | Eng Lead | Not started | Jul 8
| Security sign-off | Security | Not started | Jul 8
| Support readiness sign-off | CS Lead | Not started | Jul 8
| PM final go | Lena | Not started | Jul 8
© PM Toolkit by Neelesh Singh · neeleshpmtoolkit.com — Free for personal use. Adapt freely; please keep the credit line.

## Release Notes — Example
RELEASE NOTES · METERLY
Smart Dunning v1 — customer-facing
PM Toolkit by Neelesh Singh · neeleshpmtoolkit.com
Meterly · Smart Dunning v1 · Released Jul 8, 2026
Recover more failed payments — automatically. Smart Dunning retries failed charges intelligently and prompts customers to update expiring cards, so you keep revenue customers never meant to stop paying.
NEW
• Smart retries — failed charges now retry on an intelligent schedule, recovering significantly more revenue with zero manual work
• Pre-dunning card reminders — customers are nudged to update an expiring card before a payment fails
• One-click card update — a secure hosted page lets customers fix a failed payment in seconds
IMPROVED
• Recovery dashboard — track recovered revenue and recovery rate by cohort, in real time
FIXED
• Webhook reliability — resolved a signature mismatch on charge.recovered events
ACTION NEEDED
• Turn it on — enable Smart Dunning in Settings → Billing → Recovery (pilot accounts are on by default)
COMING NEXT
• Adaptive timing & SMS — ML-tuned retry timing and SMS reminders for high-value accounts
Questions? Visit help.meterly.com or reply to this email — we read every one.
© PM Toolkit by Neelesh Singh · neeleshpmtoolkit.com — Free for personal use. Adapt freely; please keep the credit line.

## Launch Checklist — Blank
LAUNCH CHECKLIST · [PRODUCT]
Coordinate the launch; gate the go-live
PM Toolkit by Neelesh Singh · neeleshpmtoolkit.com
Release / version
Target launch date
Release owner
Launch tier
READINESS
| Overall readiness | 0% | Go / No-Go | Not ready
CHECKLIST (by workstream)
| Item | Owner | Status | Due | Notes
[Workstream]
[Checklist item]
[Checklist item]
[Checklist item]
[Workstream]
[Checklist item]
[Checklist item]
[Checklist item]
[Workstream]
[Checklist item]
[Checklist item]
[Checklist item]
[Workstream]
[Checklist item]
[Checklist item]
[Checklist item]
© PM Toolkit by Neelesh Singh · neeleshpmtoolkit.com — Free for personal use. Adapt freely; please keep the credit line.

## Release Notes — Blank
RELEASE NOTES · [PRODUCT]
What changed, in plain language
PM Toolkit by Neelesh Singh · neeleshpmtoolkit.com
[Product] · [Release] · [Date]
[One-line summary: the single most important thing this release does for the customer.]
NEW
• [What changed] — [why it matters to the customer]
IMPROVED
• [What changed] — [why it matters to the customer]
FIXED
• [What changed] — [why it matters to the customer]
ACTION NEEDED
• [What changed] — [why it matters to the customer]
COMING NEXT
• [What changed] — [why it matters to the customer]
[Where to get help / contact / changelog link]
© PM Toolkit by Neelesh Singh · neeleshpmtoolkit.com — Free for personal use. Adapt freely; please keep the credit line.