## How to Use
SPRINT PLANNING & RETRO BOARD
Plan against real capacity, run the sprint, close the loop with a retro that ends in actions
PM Toolkit by Neelesh Singh · neeleshpmtoolkit.com
What this is
One workbook for the whole sprint: a planning board that checks your commitment against capacity, and a retrospective that turns talk into owned action items. Built so two weeks feel structured, not scrambled.
How to use it
1. Open “Sprint Plan — Example”. It’s a real Meterly sprint: the squad shipping pre-dunning card-update prompts to a pilot cohort. Notice the load indicator flags when you over-commit.
2. Set your velocity and capacity (blue), then list the work. Points, status and completion roll up automatically; status cells colour themselves.
3. At sprint’s end, run “Retro — Example”. Keep it blameless. Every theme that matters should leave as an action item with an owner and a date — that’s the part most teams skip.
4. Copy the “— Blank” tabs each sprint (or duplicate the file). Dropdowns and formulas are already wired.
Make it yours
Swap the work-item types, status labels and point scale for whatever your team uses (t-shirt sizes, hours, Kanban states). The capacity maths and roll-ups don’t care what units you choose.
Colour legend
Blue = your input. Black = calculated. Status cells colour by value (green done, amber in-flight, red blocked).
© PM Toolkit by Neelesh Singh · neeleshpmtoolkit.com — Free for personal use. Adapt freely; please keep the credit line.

## Sprint Plan — Example
SPRINT PLAN · METERLY
Sprint 24 — Smart Dunning pilot
PM Toolkit by Neelesh Singh · neeleshpmtoolkit.com
| Sprint | Sprint 24 |  | Dates | Jun 16 – Jun 27
| Goal | Ship pre-dunning card-update prompts to the 9-account pilot cohort and instrument failed-payment recovery rate.
| Team | Aisha, Marco, Dvij, Lena (PM)
CAPACITY
| Reference velocity (3-sprint avg, pts) |  |  |  | 30
| Planned capacity this sprint (pts) |  |  |  | 28
| Committed this sprint (pts) |  |  |  | 29
| Load (committed ÷ capacity) |  |  |  | 103.6%
SPRINT BACKLOG (the commitment)
| ID | Work item | Type | Pts | Owner | Status | Notes / blockers
| SD-101 | Card-expiry detection job (flag tokens expiring ≤30 days) | Story | 5 | Dvij | Done
| SD-102 | Pre-dunning email + in-app banner | Story | 5 | Aisha | In review
| SD-103 | One-click hosted card-update flow | Story | 8 | Marco | In progress | Bigger than estimated
| SD-104 | Recovery-rate instrumentation + pilot dashboard | Story | 3 | Lena | In progress | Was blocked on analytics access
| SD-105 | PSP card-updater API spike | Spike | 2 | Dvij | Done | De-risked the integration
| SD-106 | Idempotency on retry endpoint (dedupe charges) | Tech debt | 3 | Marco | To do
| SD-107 | Fix: webhook signature mismatch on charge.recovered | Bug | 2 | Aisha | Done
| SD-108 | Pilot cohort config + feature flag | Chore | 1 | Lena | Done
| TOTAL / DONE / COMPLETION |  |  | 29 | 10 | 34.48%
Committed pts roll up live; “Done” pts and completion update as you move status. Aim to land Load ≤ 100% — the example is 104%, a deliberate nudge to cut scope.
© PM Toolkit by Neelesh Singh · neeleshpmtoolkit.com — Free for personal use. Adapt freely; please keep the credit line.

## Retro — Example
SPRINT RETRO · METERLY
Sprint 24 — blameless review → owned actions
PM Toolkit by Neelesh Singh · neeleshpmtoolkit.com
| Sprint | Sprint 24 | Facilitator / date | Lena · Jun 27
| Metrics recap | Committed 29 pts · completed 10 · 2 stories carried over · pilot live for 9 accounts
THE BOARD (keep it blameless — about the system, not the people)
| What went well | What slowed us down | What we’ll try next
| Pilot feature flag let us ship safely behind a gate | Hosted card-update flow was bigger than 8 pts | Split UI stories to ≤ 5 pts before committing
| PSP card-updater spike de-risked the integration early | Recovery dashboard blocked 2 days on analytics access | Request data/analytics access during refinement, not mid-sprint
| Pairing fixed the webhook signature bug in a day | Two stories carried over into next sprint | Add “spike before estimate” to Definition of Ready
| Daily 10-min standup kept blockers visible | Refinement ran long — vague acceptance criteria | Write Gherkin AC during refinement, not after
ACTION ITEMS (every theme that matters leaves with an owner)
| Action |  | Owner | Due | Status
| Add a story-splitting check (≤ 5 pts) to the Definition of Ready |  | Lena | Next refinement | To do
| Request analytics access for new dashboards at sprint planning |  | Marco | This sprint | Done
| Re-estimate the remaining dunning UI stories before committing |  | Aisha | Mon | In progress
| Open actions |  | 2
© PM Toolkit by Neelesh Singh · neeleshpmtoolkit.com — Free for personal use. Adapt freely; please keep the credit line.

## Sprint Plan — Blank
SPRINT PLAN · [TEAM]
Plan the sprint against capacity
PM Toolkit by Neelesh Singh · neeleshpmtoolkit.com
| Sprint |  |  | Dates
Goal
Team
CAPACITY
Reference velocity (3-sprint avg, pts)
Planned capacity this sprint (pts)
| Committed this sprint (pts) |  |  |  | 0
| Load (committed ÷ capacity) |  |  |  | 0%
SPRINT BACKLOG (the commitment)
| ID | Work item | Type | Pts | Owner | Status | Notes / blockers
| TOTAL / DONE / COMPLETION |  |  | 0 | 0 | 0%
Committed pts roll up live; “Done” pts and completion update as you move status. Aim to land Load ≤ 100% — the example is 104%, a deliberate nudge to cut scope.
© PM Toolkit by Neelesh Singh · neeleshpmtoolkit.com — Free for personal use. Adapt freely; please keep the credit line.

## Retro — Blank
SPRINT RETRO · [TEAM]
Reflect, then commit to actions
PM Toolkit by Neelesh Singh · neeleshpmtoolkit.com
| Sprint |  | Facilitator / date
Metrics recap
THE BOARD (keep it blameless — about the system, not the people)
| What went well | What slowed us down | What we’ll try next
ACTION ITEMS (every theme that matters leaves with an owner)
| Action |  | Owner | Due | Status
| Open actions |  | 0
© PM Toolkit by Neelesh Singh · neeleshpmtoolkit.com — Free for personal use. Adapt freely; please keep the credit line.