## Start Here
STAKEHOLDER MAP & COMMUNICATION PLAN
How to use this workbook
PM Toolkit by Neelesh Singh · neeleshpmtoolkit.com
What this is
Four linked tools to make stakeholder work deliberate instead of accidental: a register that auto-classifies everyone on a power/interest grid, the grid itself, a RACI for decisions, and a communication plan. The worked example follows “Meterly” (a fictional billing & payments SaaS) launching EU payments + smart dunning.
1) Power / Interest grid (Mendelow)
| Manage closely | High power + high interest. Engage fully, co-create, no surprises.
| Keep satisfied | High power, lower interest. Keep them happy; don't drown them in detail.
| Keep informed | Lower power, high interest. Update often — they're your allies and early warning system.
| Monitor | Low power, low interest. Light touch.
Score Power and Interest 1–5 in the Register; the Quadrant column classifies each person automatically (threshold = 3). Also track current vs desired stance — the gap is your influence plan.
2) RACI (per decision, not per person)
| R | Responsible — does the work.
| A | Accountable — owns the outcome. Exactly ONE per row (the A-count column checks this).
| C | Consulted — asked before the decision.
| I | Informed — told after.
3) Communication plan
For each audience: the message, the channel, the cadence, and who owns it. The fastest way to lose a stakeholder is the wrong cadence — too little and they feel blindsided, too much and they tune out.
How to use the file
• Start in ‘Register — Example’ and ‘Power–Interest Grid’ to see it populated, then work in the ‘— Blank’ tabs.
• Edit only the blue cells (scores, R/A/C/I). Quadrants and A-counts calculate themselves.
• Revisit every planning cycle — power and interest shift as a project moves.
© PM Toolkit by Neelesh Singh · neeleshpmtoolkit.com — Free for personal use. Adapt freely; please keep the credit line.

## Register — Example
STAKEHOLDER REGISTER
Map power × interest, set the engagement strategy — the quadrant fills itself
PM Toolkit by Neelesh Singh · neeleshpmtoolkit.com
# | Stakeholder / role | Group | Power (1–5) | Interest (1–5) | Quadrant (auto) | Current stance | Desired stance | What they care about | Engagement strategy | Owner | Cadence
1 | CEO | Exec | 5 | 4 | Manage closely | Supporter | Champion | Growth, NRR, board narrative | Tie to company growth story; monthly 1:1 | PM | Weekly 1:1
2 | CFO | Exec | 5 | 5 | Manage closely | Neutral | Champion | Payback, margin, compliance, cash | Co-own the business case & model | PM | Weekly 1:1
3 | VP Engineering | Eng | 4 | 5 | Manage closely | Supporter | Champion | Capacity, tech risk, sequencing | Joint planning; protect the team | PM | Biweekly steering
4 | CRO / VP Sales | GTM | 4 | 5 | Manage closely | Champion | Champion | EU pipeline unblock, win rate | Feed pipeline data; enablement | PM | Biweekly steering
5 | Head of Customer Success | GTM | 3 | 5 | Manage closely | Champion | Champion | Churn, adoption, recovery wins | Co-design pilot; share wins | PM | Biweekly
6 | Head of Compliance & Security | Risk | 4 | 4 | Manage closely | Skeptic | Supporter | PSD2/SCA, PCI, SOC 2 scope | Bring in early; sign-off gates | PM | Monthly review
7 | Board / Investors | Exec | 5 | 2 | Keep satisfied | Neutral | Supporter | Capital efficiency, EU TAM | Quarterly update via CEO | CEO | Quarterly
8 | Legal Counsel | Risk | 3 | 2 | Keep satisfied | Neutral | Neutral | DPAs, GDPR, contracts | Loop in for EU data & terms | PM | As needed
9 | Payment partner (PSP / bank) | External | 4 | 2 | Keep satisfied | Supporter | Supporter | Volume, integration scope | Keep satisfied; clear roadmap | Eng lead | Monthly
10 | Design-partner customers (9) | External | 3 | 5 | Manage closely | Champion | Champion | Recover lost revenue, fewer failures | Tight pilot loop; co-create | PM | Biweekly pilot
11 | Head of Design | Product | 2 | 4 | Keep informed | Supporter | Supporter | Portal UX, dunning comms | Involve in flows; share research | PM | Sprint review
12 | Data / Analytics lead | Product | 2 | 3 | Keep informed | Neutral | Supporter | Recovery metrics, dashboards | Define metrics together | PM | Monthly
13 | Support team lead | GTM | 2 | 4 | Keep informed | Neutral | Supporter | Ticket volume from failures | Enable; pre-empt FAQs | CS lead | Monthly
14 | Marketing lead | GTM | 2 | 2 | Monitor | Neutral | Neutral | Launch narrative | Keep informed; launch assets | PMM | At milestones
15 | EU Regulator (indirect) | External | 4 | 1 | Keep satisfied | Neutral | Neutral | PSD2 / SCA conformance | Stay compliant; monitor | Compliance | Monitor
© PM Toolkit by Neelesh Singh · neeleshpmtoolkit.com — Free for personal use. Adapt freely; please keep the credit line.

## Power–Interest Grid
POWER / INTEREST GRID
Mendelow matrix — plotted from the Register (Power = Y, Interest = X)
PM Toolkit by Neelesh Singh · neeleshpmtoolkit.com
| Key |  | Quadrants
| 1 | CEO | Manage closely | High power, high interest — engage fully, co-create.
| 2 | CFO | Keep satisfied | High power, lower interest — keep happy, don't overload.
| 3 | VP Engineering | Keep informed | Lower power, high interest — update often; useful allies.
| 4 | CRO / VP Sales | Monitor | Low power, low interest — light touch.
| 5 | Head of Customer Success
| 6 | Head of Compliance & Security
| 7 | Board / Investors
| 8 | Legal Counsel
| 9 | Payment partner (PSP / bank)
| 10 | Design-partner customers (9)
| 11 | Head of Design
| 12 | Data / Analytics lead
| 13 | Support team lead
| 14 | Marketing lead
| 15 | EU Regulator (indirect)
© PM Toolkit by Neelesh Singh · neeleshpmtoolkit.com — Free for personal use. Adapt freely; please keep the credit line.

## RACI — Example
RACI MATRIX
Responsible · Accountable · Consulted · Informed — exactly one A per row
PM Toolkit by Neelesh Singh · neeleshpmtoolkit.com
Activity / decision | PM (Product) | Eng | Design | CS | Sales / CRO | Compliance / Sec | Finance / CFO | Legal | CEO | A count
Define EU payments & dunning requirements | A | C | C | C | C | C | I | I | I | 1
PSD2 / SCA & PCI compliance sign-off | C | C | I | I | I | A | C | C | I | 1
Pricing for the recovery add-on | R | I | I | C | C | I | A | I | C | 1
Pilot with design-partner customers | A | R | C | R | C | I | I | I | I | 1
GA launch go / no-go | R | C | I | C | C | C | C | I | A | 1
Customer & release communications | A | I | C | R | C | I | I | C | I | 1
Revenue-recognition policy | C | I | I | I | I | C | A | C | I | 1
Security review / questionnaire | C | R | I | I | I | A | I | C | I | 1
Budget & headcount approval | R | I | I | I | I | I | C | I | A | 1
R = does the work · A = owns it (one only) · C = consulted before · I = informed after
© PM Toolkit by Neelesh Singh · neeleshpmtoolkit.com — Free for personal use. Adapt freely; please keep the credit line.

## Comm Plan — Example
COMMUNICATION PLAN
Who hears what, how often, from whom — keep every stakeholder in the right loop
PM Toolkit by Neelesh Singh · neeleshpmtoolkit.com
Audience | Purpose / key message | Channel | Frequency | Owner | Format | Next milestone
Board / investors | EU TAM, payback, progress vs KRs | Board meeting | Quarterly | CEO | Deck | Q-end review
Exec steering group | Progress, risks, decisions needed | Live meeting + notes | Biweekly | PM | 1-pager | Next steering
Engineering team | Scope, sequencing, blockers | Sprint planning / review | Each sprint | Eng lead | Board + standup | Sprint start
Design-partner customers | Pilot progress, gather feedback | Call + shared Slack | Biweekly | PM | Live + recap | Pilot check-in
Customer Success team | Talk track, recovery wins, FAQs | Enablement session + doc | Pre-GA, then monthly | CS lead | Deck + FAQ | Pre-GA enablement
All customers | What shipped & why it matters | In-app + email | Each release | PMM | Release notes | At GA
Compliance & Legal | PSD2/SCA/PCI checkpoints | Review meeting | Monthly | Compliance | Checklist | Next checkpoint
Company all-hands | Launch milestone & impact | All-hands | At milestones | PM | Short demo | GA week
Sales team | EU enablement & positioning | Session + battlecard | Pre-GA, then monthly | CRO | Battlecard | Pre-GA
© PM Toolkit by Neelesh Singh · neeleshpmtoolkit.com — Free for personal use. Adapt freely; please keep the credit line.

## Register — Blank
STAKEHOLDER REGISTER
Map power × interest, set the engagement strategy — the quadrant fills itself
PM Toolkit by Neelesh Singh · neeleshpmtoolkit.com
# | Stakeholder / role | Group | Power (1–5) | Interest (1–5) | Quadrant (auto) | Current stance | Desired stance | What they care about | Engagement strategy | Owner | Cadence
1
2
3
4
5
6
7
8
9
10
11
12
13
14
© PM Toolkit by Neelesh Singh · neeleshpmtoolkit.com — Free for personal use. Adapt freely; please keep the credit line.

## RACI — Blank
RACI MATRIX
Responsible · Accountable · Consulted · Informed — exactly one A per row
PM Toolkit by Neelesh Singh · neeleshpmtoolkit.com
Activity / decision | PM (Product) | Eng | Design | CS | Sales / CRO | Compliance / Sec | Finance / CFO | Legal | CEO | A count
0
0
0
0
0
0
0
0
0
0
R = does the work · A = owns it (one only) · C = consulted before · I = informed after
© PM Toolkit by Neelesh Singh · neeleshpmtoolkit.com — Free for personal use. Adapt freely; please keep the credit line.

## Comm Plan — Blank
COMMUNICATION PLAN
Who hears what, how often, from whom — keep every stakeholder in the right loop
PM Toolkit by Neelesh Singh · neeleshpmtoolkit.com
Audience | Purpose / key message | Channel | Frequency | Owner | Format | Next milestone
© PM Toolkit by Neelesh Singh · neeleshpmtoolkit.com — Free for personal use. Adapt freely; please keep the credit line.